## POA&M Worksheet
# | CSAM POA&M ID # | Control ID(s) | Risk Level (VL,L,M,H, VH) | Status | Delay (Reason) | Weakness | Recommended Actions (Milestones) or Risk Acceptance Justification | Responsible POC(s) | Resources Required | Cost Justification | Scheduled Completion Date | Planned Start | Planned Finish | Actual Start | Actual Finish | Notes
1 | 55475 | IA-2(1), IA-2(2), IA-2(8), IA-2(11); IA-2(12); IA-5(2); IA-5(11) | H | Delayed | Technology delay/ dependency | REGIS is not currently PIV-enabled. Risk: Lack of PIV implementation leaves the system more vulnerable to unauthorized access, making financial data that is transmitted through REGIS more vulnerable to unauthorized disclosure and modification. | The Assessment Team recommends raising the Risk Level of this POAM from Moderate to High as the scheduled completion date for PIV compliance was September 30, 2015. The Assessment Team recommends removing IA-7 from this POAM, as REGIS does not have any cryptographic modules within its authorization boundary. The System Owner and developers have determined that MyAccess is not an option for PIV implementation; the team is researching the use of Integrated Windows Authentication (IWA) for PIV-enabled access. This POAM is delayed due to the System Owner working with the developers to determine if IWA is a suitable option to implement PIV authentication; it was determined that MyAccess was not a viable solution. | Lai Lee-Birman (REGIS System Owner) | $100 | Minimum Organizational Cost | 2016-09-30 | 2017-05-01 | 2018-05-30 | 2016-09-30 | TBD | 6/16/2016: MyAccess team will be contacting the Citrix team to implement this item 7/21/2016: Awaiting further direction 9/22/16: No change. Lai to respond to MyAccess team to see if there is any updates from their side 1/30/2017: No updates 5/10/2017: On hold. Need clarification from secuirity assesment team on how to proceed
2 | 60028 | PL-2; RA-2 | H | Delayed | Other | RA-2: During the assessment, REGIS information system data types were not validated by the Information Steward. PL-2: The System Characterization was unable to be properly updated with the most accurate system data types. Risk: The risk of not properly categorizing the system makes it difficult to understand the scope of REGIS and what the effect might be on the overall security posture of the system which may lead to improper security settings and management. | The Assessment Team recommends that the REGIS Information Steward provide additional information on the types of data that are stored and transmitted by the system, in order to correctly verify the Security Categorization. Data types should be mapped to Information Types in accordance with SP 800-60, Volume II, to verify the accuracy of the current FIPS 199 and overall FIPS 200 level of Moderate. The System Characterization should be reviewed and updated as necessary to document all changes that have been made to the system. This POAM is delayed because the REGIS Information Steward did not verify that the list of data types listed in the SCD are comprehensive, to include all data types that REGIS stores, transmits and processes. | Jeremy Holmes (REGIS Information Steward) | $100 | Minimum Organizational Cost | 2016-09-30 | 2017-05-03 | 2018-05-30 | TBD | TBD
3 | 55476 | RA-5 | H | Delayed | Other | No MVM, Db, URL or application code scans were provided for AFCA. No application code scans were provided for REGIS. REGIS: Database (DbProtect) scans were provided for FAA-AIT-JAMCDFPNDB501, which were run on 10/11/2016. The scans found 30 high, 166 medium, and 61 low vulnerabilities. The high vulnerabilities include: - Misconfigurations - Improper Access Controls - Patchable vulnerabilities - Weak Passwords REGIS: MVM scans were provided for IP addresses 172.29.70.78-.100, which were run on 12/18/2016. The scans found 92 high (four (4) unique), 91 medium (four (4) unique), and 46 low vulnerabilities. The high vulnerabilities include: - Microsoft HTML Help Stack Overflow Remote Code Execution - MS Windows Media Player Null Pointer Remote Denial of Service - MS XML Core Services Unitialized Memory Corruption Remote Code Execution - MS XML Core Services Remote Code Execution II REGIS: MVM scans were provided for IP addresses 172.29.70.78-.100, which were run on 4/18/2017. The scans found 206 high (9 unique), 229 medium (10 unique), and 46 low vulnerabilities. The high vulnerabilities are related to: - Remote Code Execution - MS Windows Media Player Null Pointer Remote Denial of Service - MS Windows Memory Handling Denial of Service REGIS vulnerabilities are not being remediated within the DOT timeframes (within 90 days for Critical/High findings, for a Moderate impact system). Risk: Without running consistent, privileged scans on the operating system, application and database levels of the information system, the stakeholders are unaware of critical vulnerabilities and therefore unable to take appropriate actions to remediate the vulnerabilities. This results in an increased security risk to the information system. | The Assessment Team recommends that: The AFCA System Owner complete scanning on all system assets (MVM, db, URL and code scans, as applicable), before the system goes into production, which is scheduled for July 2017. The REGIS and AFCA System Owners develop a vulnerability management plan that includes regular scans, reviewing of the scan results, and remediating legitimate vulnerabilities. The AFCA System Owner work with the FAA SOC and the Vulnerability Management Branch to perform the following scans at the indicated frequencies: i) Monthly privileged MVM scans on all servers within the authorization boundary ii) Monthly DB Protect scans on the database iii) Annual system application code scan iv) Annual URL scan The REGIS System Owner work with the FAA SOC and the Vulnerability Management Branch to perform the following scans at the indicated frequencies: i) Monthly DB Protect scans on the database ii) Annual system application code scan The REGIS and AFCA System Owners review the results of the scans once they are received and work with the datacenter to remediate any legitimate Critical or High vulnerabilities identified during the scans. Legitimate vulnerabilities should be remediated within the following DOT timeframes for moderate impact systems. This POAM is delayed due to the REGIS System Owner relying on the datacenter to remediate findings, and the FAA SOC to complete system scans. The REGIS and AFCA System Owners will request application code scans. | Lai Lee-Birman (REGIS System Owner) Cindy Owens (AFCA System Owner) Pamela Lundstrom (Vulnerability Management Branch) | $100 | Minimum Organizational Cost | 2015-12-31 | 2016-04-30 | 2017-09-30 | TBD | TBD | 6/16/2016: We need to fill out the forms to start the MVM and Web Inspect scan 7/21/2016: OST to fill out forms 9/22/16: Lai to send the package for latest forms 10/12/16: Forms submitted by Lai 1/30/2017: MVM scans available for Aug/Sep 2016; no DBProtect scans 5/10/2017: Vulnerabilitiy review in progress
4 |  | SI-2 | H | Planned/ Pending | Not Applicable | AFCA: WebInspect scans were not provided for the system URL: Afca.faa.gov, therefore the assessor is unable to determine that flaw remediation is occurring according to DOT timeframes. REGIS and AFCA: System Owners did not provide application code scans, therefore the assessor is unable to determine what vulnerabilities exist, and that flaw remediation is occurring according to DOT timeframes. Risk: The risk of not conducting flaw remediation on system components is that it leaves those components open to the vulnerabilities and therefore more vulnerable to attack. This can compromise the confidentiality and integrity of the data that is stored within AFCA. | The Assessment Team recommends that the AFCA System Owner work with the FAA SOC to conduct a scan of the system URL and application code before the system goes into production, which is planned for July 2017; vulnerabilities should be remediated within the DOT timeframes, and scans should be re-run to confirm that vulnerabilities have been remediated. The Assessment Team recommends that the REGIS System Owner work with the FAA SOC to conduct application code scans; vulnerabilities should be remediated within the DOT timeframes, and scans should be re-run to confirm that vulnerabilities have been remediated. | Lai Lee-Birman (REGIS System Owner) Cindy Owens (AFCA System Owner) | $100 | Minimum Organizational Cost | 2017-09-30 | 2017-05-03 | 2017-09-30 | TBD | TBD | 5/10/2017: Fill out the HP Fortify scan forms for the REGIS code scans
5 |  | CA-3; CM-7; SA-4(9); SA-9(2) | M | Planned/ Pending | Not Applicable | Port information was not provided for the REGIS interconnections with CWP and AIT EDR. Risk: Unnecessary open ports can leave REGIS PII and financial data more vulnerable to additional hacker threats by someone that is attempting to breach the system. | The Assessment Team recommends that the REGIS System Owner obtain and document all system interconnection information, including ports used for interconnections with CWP and AIT EDR; this information should be documented within the SCD. | Lai Lee-Birman (REGIS System Owner) | $100 | Minimum Organizational Cost | 2018-05-31 | 2017-05-03 | 2018-05-31 | TBD | TBD | 5/10/2017: Evidence/information has been provided
6 |  | AC-11, AC-11(1) | M | Planned/ Pending | Not Applicable | The REGIS application does not implement a session lock after 30 minutes of inactivity. The Citrix meta frame has a session lock after three (3) hours of inactivity, however, this does not comply with DOT Policy. Risk: Not implementing a session lock leaves the application vulnerable to brute force attacks and session hijacking. | The Assessment Team recommends the System Owner work to configure the system to implement a session lock of the application after 30 minutes of inactivity. The session lock should remain in place until the user re-authenticates to the system. | Lai Lee-Birman (REGIS System Owner) | $100 | Minimum Organizational Cost | 2018-05-31 | 2017-05-03 | 2018-05-31 | TBD | TBD | 6/16/2016: The account lock out has been implemented. The 30 minute session lockout implementation strategy has been submitted, but we haven't received any feedback from the business 7/21/2016: Revisited with the business on 7/20. Awaiting feedback. 9/22/16: No updates 10/12/16: No updates. ABP wants to wait until the bandwidth issues are taken care of at the Citrix level. AIT to inquire about the actual timeout of the session from Citrix. 1/30/2017: No updates 5/10/2017: On hold
7 | 60031 | AC-6(9) | M | Delayed | Other | Evidence was not provided showing that REGIS is auditing the execution of privileged functions, such as adding, deleting or modifying system users. Risk: Unauthorized account changes made by system administrators could go unnoticed, which could allow for a user account to be created, and granted privileges without proper approval. A user with unauthorized access to the financial data stored within REGIS, could make unauthorized changes, affecting both the confidentiality and integrity of the data that is stored within the system. | The Assessment Team recommends that the System Owner work with the REGIS developers to implement a mechanism to audit all privileged functions, such as adding, deleting or modifying system users; or provide evidence that this level of audit tracking is already in place. This POAM is delayed due to the System Owner working with the REGIS developers to determine if it is possible to implement a mechanism to audit privileged functions. | Lai Lee-Birman (REGIS System Owner) | 100 | Minimum Organizational Cost | 2017-04-30 | 2017-05-03 | 2018-05-30 | TBD | TBD | 1/30/2017: Awaiting further direction 5/10/2017: Working on creating the estimates on the cost of implementation
8 |  | AU-1 | M | Planned/ Pending | Not Applicable | The REGIS and AFCA System Owners did not provide documented audit procedures. Risk: The risk of not having documented audit procedures in place is that there is not a repeatable process for system administrators to follow ensuring that all activity is logged and reviewed for potential malicious activity. | The Assessment Team recommends creating documented audit review procedures to include what events are being audited within each system, how often the audit logs are reviewed, who conducts the audit reviews, where the audit/event logs are located within each system, who is notified in the event that suspicious activity is observed. | Lai Lee-Birman (REGIS System Owner) Cindy Owens (AFCA System Owner) | $100 | Minimum Organizational Cost | 2018-05-31 | 2017-05-03 | 2018-05-31 | TBD | TBD | 1/30/2017: Awaiting further direction 5/10/2017: This item follows the POAM to implement auditing on privileged actions
9 | 60032 | AU-2; AU-3; AU-3(1) | M | Delayed | Other | AU-2: The AFCA System Owner did not provide evidence that successful and unsuccessful logon events, account management, privileged functions are being captured. The REGIS System Owner did not provide evidence that unsuccessful logon events, account management, and privileged functions are being captured via audit logs. AU-3: The AFCA System Owner did not provide evidence that the identity of individuals associated with changes is being audited. AU-3(1): The AFCA System Owner did not provide evidence that it has the capability to audit session, connection, transaction, or activity duration for all user actions. AU-3(1): With the exception of the last login date, the REGIS System Owner did not provide evidence that it is auditing the user connection, session or activity duration. Risk: Audit logs are critical in the detection of malicious activity or system degradation. Lack of ability to track all user activity, including session duration can lead to security threats or incidents, as potential suspicious user activity may go unnoticed or undocumented. | The Assessment Team recommends adding AU-2 and AU-3 to this POAM, as they are related to the implementation of proper system auditing. The Assessment Team recommends that the REGIS System Owner work with the developers to implement a mechanism to audit all user activity, including the session duration, unsuccessful logon events, account management, and privileged functions; or provide evidence that this level of audit tracking is already in place. If this information can be obtained through the Citrix audit logs, since users access REGIS via a Citrix connection, this POA&M can be considered for a potential Risk Acceptance. The Assessment Team recommends that the AFCA System Owner work with the developers to update the source code to provide the ability to audit user activity, including session, connection, transaction, or activity duration for all user actions; in addition, unsuccessful logon events, account management, and privileged functions. This POAM is delayed due to lack of evidence provided showing the proper implementation of auditing controls. | Lai Lee-Birman (REGIS System Owner) Cindy Owens (AFCA System Owner) | 100 | Minimum Organizational Cost | 2017-04-30 | 2017-05-03 | 2018-05-30 | TBD | TBD | 1/30/2017: Awaiting further direction 5/10/2017: Working on creating the estimates on the cost of implementation
10 |  | CM-1; CM-9 | M | Planned/ Pending | Not Applicable | AFCA does not currently have a Configuration Management Plan (CMP) in place that addresses roles and responsibilities, as well as the configuration management processes, procedures, and configuration items within the system, that are under change control. Risk: A CMP ensures all configuration changes are properly approved and tracked; the risk of not documenting and updating a CMP is that there is no repeatable process for implementing the most current, secure baseline in the event of a system failure or the need for a roll-back. | The Assessment Team recommends that the AFCA System Owner develop a Configuration Management Plan that establishes a process for: identifying and managing AFCA configuration items throughout the SDLC, to include the location of the baseline configuration, and documented records of changes made to the configuration items and baseline configurations. In addition, the System Owner should document a change control process, which includes: the types of changes that should be managed under configuration control (hardware changes, software upgrades, etc.), who is authorized to approve changes, and records of all changes. This can all be included in a Configuration Management Plan; NIST SP 800-128 contains a sample outline and documents the process for creation of a CMP. | Cindy Owens (AFCA System Owner) | $100 | Minimum Organizational Cost | 2018-05-31 | 2017-05-03 | 2018-05-31 | TBD | TBD
11 | 57959 | CP-2, CP-2(3), CP-2(8) | M | Delayed | Not Applicable | CP-2: The REGIS System Owner did not provide the detailed recovery procedures for the REGIS Information System Contingency Plan (ISCP). CP-2, 2(3) 2(8): The AFCA System Owner did not provide an ISCP for review, which includes evidence that a Business Impact Analysis (BIA) has been completed; the BIA should include mission essential system assets. Risk: Without an updated ISCP, REGIS and AFCA are at risk of additional downtime after a system failure, as key personnel may not be aware of the process for recovering the system to a last known good configuration. | The Assessment Team recommends raising the Risk Level of this POAM to Moderate (from Low), as AFCA has not documented an ISCP or BIA. The Assessment Team recommends removing CP-2(1) from this POAM, as that control is now handled at the enterprise level by the Continuity Management branch. The Assessment Team recommends that the AFCA System Owner work with the Continuity Management Branch to: - Review and update the ISCP - Complete a BIA and ensure essential missions and business functions and assets are identified within the BIA, and a plan documented for the resumption of these functions. The Assessment Team recommends that the REGIS System Owner work with the Continuity Management Branch to: - Update the ISCP to include detailed recovery procedures. This POAM is delayed because the REGIS System Owner has not defined the detailed recovery procedures within the ISCP. | Lai Lee-Birman (REGIS System Owner) Cindy Owens (AFCA System Owner) Gary Robinson (Continuity Branch) | 100 | Minimum Organizational Cost | 2016-09-30 | 2017-03-01 | 2018-05-30 | 2017-03-01 | TBD | 6/16/2016: Tier3 to review the ISCP and BIA and perform the table-top 7/21/2016: Action is on AIT and the business, OST to support as needed 9/22/16: No updates 10/12/16: AIT met with Aubrey; AIT/ABP to review the ISCP 1/30/2017: No updates 5/10.2017: AIT to address
12 |  | CP-3; CP-4; IR-3 | M | Planned/ Pending | Not Applicable | CP-3: The AFCA System Owner did not complete ISCP training. CP-4: The AFCA System Owner has not provided evidence that it has undergone a table-top ISCP test during the FY17 security assessment; AFCA is a low availability system. IR-3: The AFCA System Owners did not provide evidence that Incident Response testing has been conducted in FY17, or that an incident handling process is in place. Risk: The associated risk is that all key personnel may not know how to recover the system to a known state after a disruption, compromise, or failure. | The Assessment Team recommends that the AFCA System Owner continue to work with the Continuity Management Branch to schedule a complete a table-top exercise for the AFCA application; this test should include training. All results should be documented within the ISCP and ISCP Test and Results document. The Assessment Team recommends that the System Owner work with the Continuity Management branch to conduct an Incident Response (IR) test. The Continuity Management branch can include IR scenarios in the ISCP table-top tests; testing includes knowing who will contact the FAA SOC, and when to contact the FAA SOC. In the event of an actual security breach, the System Owner may be required to provide audit logs, or other investigation material to the SOC. | Cindy Owens (AFCA System Owner) Gary Robinson (Continuity Management Branch) | $100 | Minimum Organizational Cost | 2017-09-30 | 2017-05-01 | 2017-09-30 | TBD | TBD
13 | 57953 | IA-5. IA-5(1) | M | Delayed | Technology delay/ dependency | The Assessment Team found that REGIS does not define password requirements or implement proper password complexity for system user accounts. Risk: Not enforcing DOT Compendium password complexity requirements for the REGIS Application user accounts, leaves the system vulnerable to adversarial brute force, dictionary and rainbow table attacks. | The Assessment Team recommends that the System Owner continue progress on implementing PIV authentication to meet DOT requirements. PIV implementation will remediate both vulnerabilities. The original recommendation is below: -The system owner develop and document a password policy including the following: The information system, for password-based authentication: (a) Enforces minimum password complexity of: Passwords must contain a minimum of twelve (12) characters and must contain a combination of: - 1 uppercase character - 1 lowercase character - 1 numeric character - 1 special character - No character may be repeated twice in sequence; Any account/user identifier requiring a blank password must only be accessible from the system console.; (b) Enforces at least the following number of changed characters when new passwords are created: At least 1 or as determined by the system; (c) Stores and transmits only cryptographically-protected passwords; (d) Enforces password minimum and maximum lifetime restrictions of 1 day minimum and 60 day maximum; (e) Prohibits password reuse for 24 generations; and (f) Allows the use of a temporary password for system logons with an immediate change to a permanent password. This POAM is delayed because the System Owner is researching options for PIV implementation using Integrated Windows Authentication; MyAccess is unable to be used in the Citrix environment. | Lai Lee-Birman (REGIS System Owner) | $100 | Minimum Organizational Cost | 2016-09-30 | 2017-05-03 | 2018-05-31 | TBD | TBD | 6/16/2016: Will have to wait on the decision with PIV enablement of the REGIS application 7/20/2016: Awaiting further direction 9/22/16: Tier3 to review this POAM and respond back to AIT 1/30/2017: OST to schedule for April release 5/10/2017: This item is dependent on the POAM to implement PIV enablement
14 | 60037 | IR-2 | M | Delayed | Other | The System Owners have not provided evidence that annual Incident Response training is occurring for REGIS or AFCA. Risk: The risk of not conducting incident response training is that system personnel are not fully aware of incident response capabilities, roles, responsibilities and guidelines. This affects REGIS personnel's capability to detect or respond to a message from the FAA SOC for any security incidents and could adversely affect the security of the application. The FY16 vulnerability is below: The REGIS System Owner does not test (IR-3) an incident response capability and key personnel are not provided incident response training (IR-2). | The Assessment Team recommends removing IR-3(2) from this POAM as that control is implemented by the FAA SOC. The Assessment Team recommends removing IR-3 from this POAM as REGIS has completed incident response testing via the completion of a Table-Top exercise. The results are documented within the ISCP Test and Results document. The Assessment Team recommends the REGIS and AFCA System Owners work with AIS-100 (Training) and AIS-300 (FAA SOC) to conduct annual Incident Response training; results of all training exercises should be properly documented, ensuring that REGIS and AFCA know how to implement incident handling in the event of a security breach. This POAM is delayed due to the System Owners waiting on the implementation of an enterprise level solution for incident response training; this is being managed through the FAA SOC. | Lai Lee-Birman (REGIS System Owner) Cindy Owens (AFCA System Owner) AIS-100 FAA SOC | $100 | Minimum Organizational Cost | 2017-04-30 | 2017-05-03 | 2018-05-31 | TBD | TBD | 6/16/2016: Create an Incident Response plan. Lai to check which elements need to be included in the document 7/21/2016: Awaiting further direction, templates/examples 9/22/16: Lai to send out the templates/examples 10/12/16: Received format; working on formulating the response plan 1/30/2017: In progress 5/10/2017: AIT to address
15 |  | SC-28 | M | Planned/ Pending | Not Applicable | The REGIS and AFCA System Owners did not provide any evidence that the databases used to support the systems are encrypted. Risk: The risk associated with not encrypting the system data at rest, is the confidentiality and integrity of REGIS and AFCA data is more vulnerable to hackers, or other unauthorized user access with the motive for malicious intent. | The Assessment Team recommends that the System Owners research options for ensuring that the REGIS and AFCA data at rest is encrypted. | Lai Lee-Birman (REGIS System Owner) Cindy Owens (AFCA System Owner) | $100 | Minimum Organizational Cost | 2018-05-31 | 2017-05-03 | 2018-05-31 | TBD | TBD | 5/10/2017: Will need to coordinate with Glenn Sprinkle (sys DBA) regarding this POAM
16 |  | SC-8; SC-8(1) | M | Planned/ Pending | Not Applicable | The AFCA URL (afca.faa.gov) is not currently encrypted. Risk: Traffic between users and web server can be sniffed for username and password if sniffer is on the internal FAA network. The same applies for data passed between databases. | The Assessment Team recommends the AFCA System Owner work with the team that is responsible for managing the web application to implement modern cryptography to establish secure connections between users and http://AFCA.FAA.GOV, to protect sensitive system data in transit. | Cindy Owens (AFCA System Owner) | $100 | Minimum Organizational Cost | 2018-05-31 | 2017-05-03 | 2018-05-31 | TBD | TBD
17 | 60038 | SI-10 | M | Completed | Not Applicable | The FY16 vulnerability is below: REGIS did not provide any evidence that data validation tools are being used. Risk: When software does not validate input properly, an attacker is able to craft the input in a form that is not expected by the rest of the application. This will lead to parts of the system receiving unintended input, which may result in altered control flow, arbitrary control of a resource, or arbitrary code execution. | The Assessment Team recommends that this POAM be closed as "Completed" in CSAM. The REGIS System Owner has provided evidence that the system includes a data validation capability; screenshots are provided within "REGIS Assessment Meeting 1 notes and screenshots" which is located in the REGIS FY17 Working Documents folder on KSN. | Lai Lee-Birman (REGIS System Owner) | $100 | Minimum Organizational Cost | 2017-04-30 | 2016-04-30 | 2017-04-30 | 2017-04-01 | 2017-05-03 | 5/10/2017: Completed
18 |  | AC-1; AC-2 | L | Planned/ Pending | Not Applicable | REGIS and AFCA System Owners did not provide documented procedures detailing how account management is handled, including defining procedures for how system accounts, for each user type, are created, enabled, modified, disabled, and removed. Risk: The risk associated with not having current documented procedures for account management in place is that changes may have occurred in the process or procedures, and if undocumented, there is no repeatable process for ensuring that all account management activity is being handled correctly. | The Assessment Team recommends that the REGIS and AFCA System Owners document account management procedures, detailing how user access, including administrator access is granted; this should include the entire approval process, and what forms are required for access. In addition, the REGIS and AFCA teams should document the account management process including defining procedures for how system accounts, for each user type (including administrators), are created, enabled, modified, disabled, and removed. This documentation should include all tools that are used to track system user access, such as Remedy; these procedures can be included in one "Account Management SOP". | Lai Lee-Birman (REGIS System Owner) Cindy Owens (AFCA System Owner) | $100 | Minimum Organizational Cost | 2018-05-31 | 2017-05-03 | 2018-05-31 | TBD | TBD | 6/16/2016: Will have to wait on the decision with PIV enablement of the REGIS application 7/21/2016: Awaiting further direction 9/22/16: Tier3 to review and analyze the requirements 10/12/16: No updates 1/30/2017: OST to develop estimate for implementation; need definition of "appropriate individuals" to receive notifications 5/10/2017: Find the form filled out to request access to the application servers. Create a document to explain the process
19 | 57956 | AC-2(3) | L | Existing Risk Acceptance | Not Applicable | REGIS does not disable inactive accounts at the database level. Risk: Without implementing this control could lead to unauthorized access to the system database and violation of the concept of least privileges. | The Assessment Team reviewed this risk item with the System Owner during the FY17 assessment and recommends the risk be reaccepted. The database accounts and application level accounts are built into accounts that are necessary for the functionality of the system. There are a limited number of data admin accounts and these accounts are based on FAA Active directory accounts, which are automatically deactivated after a period of inactivity. User accounts at the application level are using the FAA Active Directory (AD) lookup to authenticate into the application. All AD accounts are disabled after 90 days of inactivity. | Sean Torpey, AIT-001 | 0 | (Risk Acceptance Items do not require funding) | 2016-09-30 | 2016-04-30 | 2016-09-30 | 2017-05-03 | TBD
20 |  | AC-2(3) | L | Planned/ Pending | Not Applicable | AFCA did not provide evidence that system accounts are automatically disabled after 90 days of inactivity. Risk: An inactive account, yet still live with write privileges, could be compromised and used to make unauthorized changes, affecting the confidentiality and integrity of the AFCA data. | AFCA is PIV enabled via MyAccess and relies on MyAccess to disable user accounts after 90 days of inactivity. The purpose of AFCA is to serve as the official system of record for tracking the set of FAA employees who have been granted the business role of “Funds Certifier”, and does not perform any functions related to disbursement or certification of funds; all FAA federal employees have access to AFCA. The Assessment Team acknowledges that relying on MyAccess to disable the Funds Certifier user types after 90 days of inactivity is acceptable, however, all supervisor, manager and solutions administrator accounts should be automatically disabled after 90 days of inactivity. | Cindy Owens (AFCA System Owner) | $100 | Minimum Organizational Cost | 2018-05-31 | 2017-05-03 | 2018-05-31 | 2018-05-03 | TBD
21 | 55478 | AC-2(4) | L | Delayed | Other | The REGIS and AFCA System Owners did not provide evidence that all account management activity is audited, and that the system has the capability to send automatic alerts to personnel regarding account management activity. Risk: Without auditing the creation, modification, enabling, disabling and removal of information system accounts, the information System Owner will be unaware of any unauthorized activity within the information system. This increases the risk profile of the information system. | The Assessment Team recommends the REGIS and AFCA System Owners work with the system developers to implement functionality to ensure that all account management activity is audited, and alerts are send to system/solution administrators when account management activity occurs, such as a new user being added. This POAM is delayed because evidence was not provided that the control is being properly implemented; the REGIS System Owner is working with the developers to find a suitable solution to this vulnerability. | Lai Lee-Birman (REGIS System Owner) Cindy Owens (AFCA System Owner) | $100 | Minimum Organizational Cost | 2016-09-30 | 2017-05-01 | 2018-05-30 | TBD | TBD | 6/16/2016: Will have to wait on the decision with PIV enablement of the REGIS application 7/21/2016: Awaiting further direction 9/22/16: Tier3 to review and analyze the requirements 10/12/16: No updates 1/30/2017: OST to develop estimate for implementation; need definition of "appropriate individuals" to receive notifications 5/10/2017: Working on creating the estimates on the cost of implementation
22 | 57955 | AC-2, AC-2(2) | L | Canceled | Not Applicable | The FY16 vulnerability is below: Within REGIS, temporary/Guest accounts are created for the FAA SOC to perform application code scans on the system; however there are no procedures documented on how these accounts are managed, monitored, and deleted. Risk: Without the regular monitoring and review of information system accounts, inaccurate permissions and outdated roles may exist, resulting in contradictions to the principles of least privileges, separation of duty and need to know. This could result in unauthorized changes and views of the information system, which results in a higher risk profile for the information system. | The Assessment Team recommends that this POAM be closed as "Canceled" in CSAM. REGIS does not use temporary accounts; this was an incorrectly assigned POAM. The FY16 recommended action is below: The Assessment Team recommends documenting the use of temporary/guest accounts in REGIS. The assessment team also recommends that these accounts be monitored and removed in accordance with DOT policy, within five (5) days. | Lai Lee-Birman (REGIS System Owner) | 0 | NA | 2016-09-30 | 2017-05-01 | 2018-05-30 | NA | NA
23 | 57957 | AC-7 | L | Completed | Not Applicable | The FY16 vulnerability is below: The REGIS application does not enforce an account lockout after five (5) consecutive invalid logon attempts. The Citrix met frame has an account lockout managed by PIV and Active Directory, however this does not apply to the REGIS application as REGIS has a separate log in. Risk: Not implementing account lockout for invalid login attempts leaves the application vulnerable to brute force attacks and session hijacking. | The Assessment Team recommends removing AC-11 and AC-11(1) from this POAM as implementation of those controls does not relate to consecutive invalid login attempts; a separate POAM will be created to track those control vulnerabilities. The Assessment Team recommends that this POAM be closed as "Completed" in CSAM. The REGIS team provided "5-attemptConfig" as evidence that this control is now being properly implemented; the application enforces an account lockout after five (5) invalid logon attempts. The artifact is located in the FY17 REGIS Working Documents folder. The FY16 recommended actions are listed below: The Assessment Team recommends that the REGIS System Owner continuing progress on implementing PIV authentication. The system will then inherit the management of invalid logon attempts (AC-7) from FAA Directory Services and can be updated to "Completed" once PIV is implemented. | Lai Lee-Birman (REGIS System Owner) | $100 | Minimum Organizational Cost | 2016-09-30 | 2016-03-01 | 2016-09-30 | 2017-05-03 | 2017-05-03 | 5/10/2017: Completed
24 | 60039 | AC-8 | L | Completed | Not Applicable | The FY16 vulnerability is below: The REGIS application interface and Citrix-based interfaces display a warning banner that does not meet the DOT Compendium requirements for wording. Risk: The risk of not having a DOT-approved warning banner includes but is not limited to liability for the DOT in the event that malicious activity takes place on the system. If users are not presented with the warning banner they can claim that they did not know how to act on the information system or the laws to which they are subject. | The Assessment Team recommends that this POAM be closed as "Completed" in CSAM. REGIS has updated their warning banner to be in compliance with DOT requirements, as shown in "REGIS Assessment Meeting 1 notes and screenshots". The banner includes the verbiage "by using this information system you are consenting to the following…" and you must select "Login" to access the system. The artifact is located in the REGIS FY17 Working Documents folder. | Lai Lee-Birman (REGIS System Owner) | $100 | Minimum Organizational Cost | 2017-04-30 | 2016-04-30 | 2017-04-30 | 2017-03-01 | 2018-05-03
25 |  | AC-8 | L | Planned/ Pending | Not Applicable | AFCA does not have a warning banner that meets DOT requirements, that must be accepted before the user can access the system. Risk: The risk of not having a DOT-approved warning banner includes but is not limited to liability for the DOT in the event that malicious activity takes place on the system. If users are not presented with the warning banner they can claim that they did not know how to act on the information system or the laws to which they are subject. | The Assessment Team recommends that the AFCA System Owner work with the developers to create a warning banner that meets the listed DOT requirements, that must be accepted before the user can access the system. The DOT requirements state that the system must display to users: 1. Users are accessing a U.S. Government information system; 2. Information system usage may be monitored, recorded, and subject to audit; 3. Unauthorized use of the information system is prohibited and subject to criminal and civil penalties; and 4. Use of the information system indicates consent to monitoring and recording; b. Retains the notification message or banner on the screen until users acknowledge the usage conditions and take explicit actions to log on to or further access the information system. | Cindy Owens (AFCA System Owner) | $100 | Minimum Organizational Cost | 2018-05-31 | 2017-05-03 | 2018-05-31 | TBD | TBD
26 | 60040 | AR-2 | L | Delayed | Original completion time underestimated | The REGIS PTA was adjudicated by the DOT Privacy Office on May 30, 2013; the DOT Privacy Office determined a PIA is not required. The PTA expired on May 30, 2016; a new draft PTA has not yet been completed. AFCA does not currently have an adjudicated PTA. Risk: By not having an updated PTA in place stakeholders will not know the extent of PII residing on the system. Therefore, stakeholders will not know the level of security controls required for the system and the system's overall risk posture. | The Assessment Team recommends the System Owners, AIS, FAA Privacy Office, and the DOT Privacy Office finish updating the PTA. Milestone A: The System Owners should continue to work with the AIS Privacy POC to finalize the PTA. Milestone B: The AIS Privacy POC should submit the finalized PTA to the FAA Privacy Office. Milestone C: The FAA Privacy Office should review and submit the PTA to the DOT Privacy Office. Milestone D: The DOT Privacy Office should review and adjudicate the updated PTA to determine whether a Privacy Impact Assessment (PIA) is required. This POAM is delayed because the estimated completion time was underestimated for the completion of the REGIS PTA. | Jeremy Holmes (REGIS Information Steward); Cindy Owens (AFCA System Owner); Essie Bell (AIS Privacy POC); Barbara Stance (FAA Privacy Office); Claire Barrett (DOT Privacy Office) | 100 | Minimum Organizational Cost | 2016-09-30 | 2017-05-03 | 2018-05-31 | TBD | TBD
27 | 60041 | AT-3 | L | Delayed | Dependency on other task(s) | The REGIS System Owner has identified the following individuals as Key Information System Security (ISS) Personnel to the Policy, Training & Customer Liaison Branch (AIS-110) to track their role-based security training: • Jeremy Holmes, Information Steward • Trinette Tucker - Business Analyst (Backup IS) The AFCA Project Manager has identified the following individuals as Key Information System Security (ISS) Personnel to the Policy, Training & Customer Liaison Branch (AIS-110) to track their role-based security training: • Cindy Owens, SO/IS • Matthew Clemente, Helpdesk/Incident Handler • Charles Chaconas, Helpdesk/Incident Handler • Karyl Cooper, Helpdesk/Incident Handler; Programmer/Developer • Dorian (Drew) Gattis, Programmer/Developer • Prashant Gijare, DBA/Info Sec Architect • Bhanu Katuri, Programmer/Developer Risk: Individuals that are not identified as Key Information System Security (ISS) Personnel to a particular system could potentially be missing additional training required for their elevated access and role. This increases the risk of a vulnerability being introduced as a result of insider threat, resulting from unintentional actions being performed by individuals with elevated access to the system or system information. | The request to AIS-110 to add the REGIS key personnel can be found within "FW FAA Key ISS and Privacy Personnel Specialized Role-Based Training REGIS"; however, the names have not yet been added to the Key Personnel Training list. The request to AIS-110 to add the AFCA key personnel can be found within "FW FY17 Annual Role Based Security Training "; however, the names have not yet been added to the Key Personnel Training list. The Assessment Team recommends that the System Owners follow up with AIS-110 via the AIS Governance Training mailbox: 9-AWA-AIT-AIS-Governance-Training@FAA.GOV to ensure that the required personnel are added to the list, in order to receive annual security role based training. In addition, the System Owner should notify AIS-110 as Key ISS Personnel transition into and out-of these roles: - before authorizing access to the information system; - when required by personnel or system changes; and - annually during the AIS data call. This POAM is delayed because the System Owners are waiting on AIS-110 to add the provided list of users to the Key Personnel Training List. | Lai Lee-Birman (REGIS System Owner) Cindy Owens (AFCA System Owner) AIS-110 | $100 | Minimum Organizational Cost | 2016-09-30 | 2017-04-01 | 2018-05-31 | 2017-04-01 | TBD | 5/10/2017: AIT to address
28 | 57958 | AU-6 | L | Delayed | Other | The REGIS and AFCA System Owners have not defined what unusual activity to look for when reviewing audit logs, or provided evidence that audit logs are being reviewed monthly, as required per the DOT Cybersecurity Compendium. Risk: Audit logs are critical in the detection of malicious activity or system degradation; lack of audit review can lead to security threats or incidents, or system failure going undetected. | The Assessment Team recommends that the System Owners define what unusual activity to look for during audit reviews, and provide evidence that audit records are being reviewed monthly to detect suspicious audit occurrences. A spreadsheet could be used to conduct the monthly audit reviews, showing who reviewed the logs, what logs were reviewed, the date of review, and any potential suspicious activity that may have been found. Any suspicious activity should then be reported to the FAA SOC. This POAM is delayed, because the REGIS System Owner is still in the process of detailing what unusual activity to look for during audit reviews. | Lai Lee-Birman (REGIS System Owner) Cindy Owens (AFCA System Owner) | $100 | Minimum Organizational Cost | 2016-09-30 | 2017-05-03 | 2018-05-30 | TBD | TBD | 6/16/2016: Business and assessor should give more details on how to implement this POAM 7/21/2016: Awaiting further direction 9/22/16: Lai to follow up on this POAM 10/12/16: No updates 1/30/2017: No updates 5/10/2017: Need direction on how to progress
29 | 55479 | CA-3 | L | Completed | Not Applicable | The FY16 vulnerability is below: REGIS receives information from Delphi through a connection with the Office of Information Technology Enterprise Data Repository (AIT EDR) system. This data connection requires an MOU. The Tertiary MOU with the AIT EDR is expired and the new MOU has not been completed. In addition, the port information for the system interconnections with EDR and CWP were not provided. Risk: Not properly documenting all system connections, as well as not maintaining ISA/MOUs creates a risk, as there is no acknowledgement of terms of agreement for the security measures that are required to be in place for the data exchange that is maintained between the systems. | The Assessment Team recommends that this POAM be closed as "Completed" in CSAM. The MOU between AIT EDR and REGIS has been provided. "REGIS_MOA" is located in KSN in the REGIS FY17 Working Documents folder. | Lai Lee-Birman (REGIS System Owner) | 500 | Labor Cost | 2016-09-30 | 2016-03-31 | 2016-09-30 | 2016-03-31 | 2018-05-03
30 | 60042 | CA-5 | L | Completed | Not Applicable | The FY16 vulnerability is below: The System Owner does not review and update POA&Ms on a quarterly basis. Risk: Without reviewing and updating the POA&Ms periodically, the information system cannot address the system vulnerabilities based on the defined milestones effectively. This inhibits the timely mitigation and remediation of identified system vulnerabilities. | The Assessment Team recommends that this POAM be closed as "Completed" in CSAM. REGIS POA&M items are being reviewed at least quarterly. The System Owner provided feedback on the status of POA&M items as shown in "FY16Q3_REGIS_POAM_Remediation_Status"", which is located in the REGIS FY17 Working Documents Folder. According to direction from the Vulnerability Management branch, System Owners must provide two quarterly updates in a row (including the assessment period) in order to officially "Complete" the POAM for this control; REGIS has met that requirement. | Lai Lee-Birman (REGIS System Owner) Jeremy Holmes (REGIS Information Steward) Pamela Lundstrom (Vulnerability Management Branch) | $100 | Minimum Organizational Cost | 2016-09-30 | 2016-04-30 | 2016-09-30 | 2016-10-01 | 2017-04-30
31 | 60043 | CM-4 | L | Completed | Not Applicable | The FY16 vulnerability is listed below: During the FY16 assessment it was indicated that REGIS had upgraded its Windows 2003 servers to Windows 2008, however, a Security Impact Analysis (SIA) was not completed. Risk: In addition to the completion of a SIA prior to change implementation being a NIST and FAA requirement, the risk of not properly analyzing changes to the system before implementing them could result in changes being made that can negatively impact the production environment. For example, will the upgrades affect how users access the system, or the system's auditing capabilities? | The Assessment Team recommends that this POAM be closed as "Completed" in CSAM. The REGIS System Owner provided "FY16 FAA Security Impact Analysis Template_REGIS", which includes the impact analysis of the server upgrades. The document can be found in the FY17 REGIS Working Documents folder on KSN. | Lai Lee-Birman (REGIS System Owner) | $100 | Minimum Organizational Cost | 2017-04-30 | 2017-05-01 | 2017-04-30 | 2017-02-01 | 2017-02-01
32 | 60044 | PL-2: SA-9(2) | L | Canceled | Not Applicable | The FY16 vulnerability is below: REGIS did not provide feedback in order to properly update the System Characterization Document, including review of the specific data types (Section 2.3); in addition, the ports used for the AIT EDR and CWP system interconnections were not documented. Risk: In order for REGIS to meet FAA and FISMA requirements, it is necessary to ensure all system security documentation is complete and accurate; all security requirements and system functionality should be properly documented. | The Assessment Team recommends that this POAM be closed as "Canceled" in CSAM. This POAM is a duplicate POAM. PL-2 has been added to POAM #60028 and SA-9(2) has been added to a new POAM regarding lack of port information being provided. The FY16 recommended actions are below: The Assessment Team recommends that the REGIS team update the SCD to include the most current system information, specifically Sections 2.3 - updating the specific data types, and Section 2.10 - adding the ports used for the CWP and AIT EDR system interconnections. | Lai Lee-Birman (REGIS System Owner) Jeremy Holmes (REGIS Information Steward) | 0 | NA | 2017-04-30 | 2016-04-01 | 2017-04-30 | NA | NA
33 | 55480 | SI-12 | L | Canceled | Not Applicable | The FY16 vulnerability is below: The Assessment Team was unable to determine whether REGIS is following the approved FAA Financial Records Disposition Schedule as the System Owner did not provide documentation to show compliance. In addition, the control implementation description doesn't adequately document the records retention information available in the Request for Records Disposition Authority for financial records available in the document "FAA Financial Records Disposition Schedule.pdf" Risk: Not following the FAA Financial Records Disposition schedule for record handling and retention leaves the organization vulnerable to legal action. | The Assessment Team recommends that this POAM be closed as "Canceled" in CSAM. The POAM was created in error during the last assessment. The REGIS System Owner explained during the assessment meetings that REGIS maintains data indefinitely. | Lai Lee-Birman (REGIS System Owner) | 0 | NA | 2016-09-30 | 2016-04-30 | 2016-09-30 | NA | NA

## Status-descriptio-Do not Delete
POA&M Status
Planned/ Pending | For new or existing POA&Ms where remediation has not started; Scheduled Completion Date cannot be past due
Canceled | For POA&Ms you are canceling or combining - needs strong justification. POA&Ms should be canceled if a common control was incorrectly identified as system responsibility or if you're consolidating controls into one POA&M.
Completed | For POA&Ms you are recommending be completed in CSAM - needs strong justification. Closed = implemented, can also be for if the requirement for the control has changed and the system now meets the requirement.
In Progress | For existing and new POA&Ms that are not delayed and progress has been started on the remediation
Delayed | For existing POA&Ms that are still open and have gone past the Scheduled Completion Date
Existing Risk Acceptance | For new Risk Acceptance items (including previous remediation items being updated to accept the risk)
Risk Acceptance | For Existing Risk Acceptance Items - might have been closed in CSAM already, tell AIS to re-open the POA&M in CSAm if they have not
Risk Level | Existing POA&Ms | [5 empty] | New POA&Ms |  | Total
| Complete | Canceled | Planned/Pending | In Progress | Delayed | Risk Acceptance | Planned/Pending | New Risk Acceptance
Very High | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
High | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 4
Moderate | 1 | 0 | 0 | 0 | 5 | 0 | 7 | 0 | 13
Low | 5 | 3 | 0 | 0 | 4 | 1 | 3 | 0 | 16
Very Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Open Total | 0 | 0 | 0 | 0 | 12 | 1 | 11 | 0 | 24
Grand Total | 6 | 3 | 0 | 0 | 12 | 1 | 11 | 0 | 33
# of POA&Ms currently open and Existing Risk Acceptance Items |  |  |  | 22
# of new POA&Ms and new Risk Acceptance items |  |  |  | 11
# of new findings being recommended for risk acceptance items + # of existing POA&M items that are being updated to recommend for risk acceptance] |  |  |  | 1
[# of prior risk acceptance items] |  |  |  | 0
Delay Reasons (As defined in CSAM)
Weakness priority changed
Original completion time underestimated
Funds not allocated/ Insufficient funding
Assigned funds withdrawn
Dependency on other task(s)
Contractor delay
Procurement delay
Personnel shortage
Technology delay/ dependency
Policy delay/ dependency
Moratorium on development
Other
Not Applicable

## Sheet1 (hidden)
Risk Level | Existing POA&Ms | [5 empty] | New POA&Ms |  | Total
| Complete | Canceled | Planned/ | In Progress | Delayed | Risk Acceptance | Planned/ | New Risk Acceptance
|  |  | Pending |  |  |  | Pending
Very High | 0 | 0 | 0 | 0 | 0 | 0 | IF(AND('POA&M Worksheet'!C3:C23, "")AND(COUNTIF('POA&M Worksheet'!F12:F23, 'Status-descriptio-Do not Delete'!A2)) | 0 | 0
High | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 5
Moderate | 1 | 3 | 0 | 0 | 0 | 0 | 11 | 0 | 15
Low | 1 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 6
Very Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Open Total |  |  | 0 | 1 | 0 | 0 | 17 | 1 | 19
Grand Total | 2 | 5 | 0 | 1 | 0 | 0 | 17 | 1 | 26